{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":[" 分项目投资完成情况（黄冈）","分市州规划内外项目完成情况（黄冈）"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":" 分项目投资完成情况（黄冈）","index":0,"n_rows":34,"n_cols":21,"rows_kept":34,"merged":[[0,1,0,19],[1,7,1,10],[2,0,2,2],[2,13,2,14],[2,15,2,18],[3,0,8,0],[3,1,8,1],[3,2,8,2],[3,3,8,3],[3,4,8,4],[3,5,8,5],[3,6,8,6],[3,7,8,7],[3,8,8,8],[3,9,6,10],[3,11,4,14],[3,15,4,17],[3,18,7,19],[3,20,8,20],[5,11,8,11],[5,12,8,14],[5,15,8,15],[6,16,8,16],[6,17,8,17],[7,9,8,9],[7,10,8,10],[9,1,9,5],[10,0,10,2],[11,0,11,5],[11,12,11,14],[12,0,12,2],[12,12,12,14],[13,12,13,14],[14,0,14,2],[15,12,15,14],[16,12,16,14],[17,12,17,14],[18,12,18,14],[19,12,19,14],[20,0,20,5],[21,0,21,2],[22,0,22,5],[22,12,22,14],[23,0,23,2],[23,11,23,20],[24,12,24,14],[25,12,25,14],[26,12,26,14],[27,0,27,5],[28,0,28,5],[28,11,28,19],[29,0,29,1],[29,2,29,5],[29,7,29,9],[29,11,29,14],[29,15,29,19],[30,0,30,1]],"flags":["formulas_cached_only"]}
[null,"湖北省交通物流基础设施投资统计报表（月、年报） （表1-1）"]
[{"$nulls":7},"2026-07-23"]
["填报单位：黄冈市道路运输和物流事业发展中心",{"$nulls":7}," ",{"$nulls":6},"填报单位所在地交通局（委）签章：",{"$nulls":3}," "]
["序号","项目名称及站级","投资建设单位名称","建设性质","开工时间","竣工时间","计划总投资    (万元）","自开始建设累计完成投资（万元）","本年计划投资 （万元）","自年初累计完成投资（万元）",null,"项目建设阶段、进度情况",{"$nulls":3},"建筑面积（平方米）",null,null,"前期工作批复文件",null,"备  注"]
[]
[{"$nulls":11},"建设阶段","形象进度",null,null,"自开始建设累计新增建筑面积"]
[{"$nulls":16},"其中：自本年初累计新增建筑面积","其中：本月新增建筑面积"]
[{"$nulls":9},"合计","其中：本月完成投资              "]
[{"$nulls":18},"工可","初设"]
[null,"黄冈"]
["一、使用交通部车购税资金建设项目"]
["小       计"]
["二、使用省燃油税返还资金建设项目"]
[]
["三、纳入规划未使用省部级资金建设项目"]
[1,"大别山智慧物流产业园","英山县九昇基础设施建设有限公司","续建",202306,202512,23000,21256,4514,3661,517,"二期开工","屋面钢结构安装",{"$nulls":5},"鄂规工程421124202401002号","英发改审批[2023]104号","已取得土地证"]
[2,"武穴市供销社集采集配综合服务中心工程","武穴市濒湖建设投资有限公司","续建",202308,202512,40000,27036.3,8000,4050.7,362.7,"开工","冷冻库主体结构及外部装修全部完成，正在进行设备招采",{"$nulls":5},"建字第179号建字第177号建字第178号","武发改审\n〔2024〕80号〔2024〕78号〔2024〕34号〔2024〕79号"]
[3,"黄州区城配中心","绿康农产品销售有限公司","续建",202409,202511,25500,4603.4,0,0,0,"开工","一期已投入运营",{"$nulls":6},"黄州发改审批[2023]57号"]
[4,"罗田县综合物流园","罗田县交通物流事业发展中心","新建",202501,202712,35000,15646.9,12000,4823.5,521.5,"开工","一期续建工程1#、2#仓库进行装修，室外配套工程进行管网施工、室外道路建设",{"$nulls":5},"罗发改审批服务[2023]80号","罗发改审批服务[2023] 88号"]
[5,"鄂东（黄冈）数智物流综合服务中心","黄冈市城投建设工程有限公司","新建",202501,202606,138764.5,53789.6,10000,16799.2,2006,"开工","分拨中心光伏板完成90%",{"$nulls":5},"黄高发审批[2024]30号","黄高发审批[2024]41号"]
["小        计",{"$nulls":5},262264.5,122332.20000000001,34514,29334.4,3407.2]
["四、农村综合服务站"]
[]
["五、使用社会资金建设项目"]
[6,"武汉北传化城市物流中心","武汉北传化公路港物流\n有限公司","续建",202112,202512,30000,19905,0,0,0,"开工","建设配套办公及食堂",{"$nulls":5},"建字第红规421122202300066",null,"已取得土地证"]
[7,"黑豹国际物流园\n（黄冈综合园区）","黑豹综合国际物流园（黄冈）有限公司/大展（浠水县）供应链有限公司","续建",202412,202611,12000,11558.1,2000,1558.1,20.2,"开工","1、2号仓库主体已全部完工，防火涂料完成50%",{"$nulls":5},"已备案","已备案","已取得土地证"]
[8,"麻城市农产品综合物流园","湖北麻乡约供应链有限公司","新建",202507,202608,35000,11509.5,10000,8235.7,1600.4,"开工","特色农产品配送中心主体结构施工完成",{"$nulls":5},"已备案","已备案"]
["小        计",{"$nulls":5},77000,42972.6,12000,9793.800000000001,1620.6000000000001]
["合        计",{"$nulls":5},339264.5,165304.80000000002,46514,39128.200000000004,5027.8]
["单位负责人：肖刚",null,"统计负责人：方毅",{"$nulls":4},"填表人：汪静",{"$nulls":3},"联系电话：07138389868",{"$nulls":3},"报出日期： 2026/7/23"]
["填报要求："]
[null,"1、本报表的统计指标解释和统计期同交通部《固定资产投资统计报表制度》；"]
[null,"2、本报表填报的项目为本年度全社会新建、改扩建项目，以前年度结转到本年度的续建项目，已竣工投产但有遗留工程尚未竣工的收尾项目；"]
[null,"3、年报表需经同级交通主管部门审核签章后向上一级运管机构报送。"]

{"sheet":"分市州规划内外项目完成情况（黄冈）","index":1,"n_rows":21,"n_cols":8,"rows_kept":21,"merged":[[0,0,0,7],[1,0,2,0],[1,1,2,1],[1,2,1,3],[1,4,1,5],[1,6,1,7],[20,0,20,1]],"flags":["formulas_cached_only"]}
["2026年全省货运（物流）基础设施投资情况表"]
["序号","市州  名称","合计",null,"规划内项目",null,"规划外的社会项目"]
[null,null,"项目个数（个）","1-7月累计完成投资  （万元）","项目个数      ( 个）","1-7月累计完成投资（万元）","项目个数      ( 个）","1-7月累计完成投资（万元）"]
[1,"武汉"]
[2,"黄石"]
[3,"十堰"]
[4,"宜昌"]
[5,"襄阳"]
[6,"鄂州"]
[7,"荆门"]
[8,"孝感"]
[9,"荆州"]
[10,"黄冈",8,39128.200000000004,5,29334.4,3,9793.800000000001]
[11,"咸宁"]
[12,"随州"]
[13,"恩施"]
[14,"仙桃"]
[15,"潜江"]
[16,"天门"]
[17,"林区"]
["合计"]