{"text_format":"3","workbook":"xls","n_sheets":5,"sheets":["SIMZNE","YESWAQ","BVSWOQ","SPRRQW","1"],"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"SIMZNE","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"hidden":true,"flags":["formulas_cached_only"]}

{"sheet":"YESWAQ","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"hidden":true,"flags":["formulas_cached_only"]}

{"sheet":"BVSWOQ","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"hidden":true,"flags":["formulas_cached_only"]}

{"sheet":"SPRRQW","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"hidden":true,"flags":["formulas_cached_only"]}

{"sheet":"1","index":4,"n_rows":22,"n_cols":20,"rows_kept":22,"merged":[[0,1,0,19],[1,0,1,3],[1,13,1,14],[1,15,1,18],[2,9,2,10],[2,11,3,14],[2,15,3,17],[3,0,7,0],[3,1,7,1],[3,2,7,2],[3,3,7,3],[3,4,7,4],[3,5,7,5],[3,6,7,6],[3,7,7,7],[3,8,7,8],[3,10,7,10],[3,18,6,19],[4,9,7,9],[4,15,7,15],[6,12,6,14],[6,16,7,16],[6,17,7,17],[8,0,8,1],[8,12,8,14],[9,12,9,14],[10,12,10,14],[11,12,11,14],[12,12,12,14],[13,12,13,14],[14,12,14,14],[16,0,16,5],[16,11,16,19],[17,7,17,9],[17,10,17,13],[17,14,17,17],[18,0,18,1]],"flags":["formulas_cached_only"]}
[null,"湖北省道路客运站场投资统计报表（月、年报）\n2026年8月 "]
["填报单位（盖章）：恩施州交通运输局",{"$nulls":7}," ",{"$nulls":10}," "]
[{"$nulls":9},"自年初累计完成投资（万元）",null,"项目建设阶段、进度情况",{"$nulls":3},"建筑面积（平方米）"]
["序  号","项目名称及站级","投资建设单位名称","建设性质","开工时间","竣工时间","计划总投资 (万元）","自开始建设累计完成投资（万元）","本年计划投资  （万元）"," ","其中：本月完成投资              ",{"$nulls":7},"前期工作批复文件"]
[{"$nulls":9},"合计",{"$nulls":5},"自开始建设累计新增建筑面积"]
[{"$nulls":16},"其中："]
[{"$nulls":11},"建设阶段","形象进度",{"$nulls":3},"自本年初累计新增建筑面积","其中：本月新增建筑面积"]
[{"$nulls":18},"工可","初设"]
["二、使用省燃油税返还资金建设项目"]
[1,"郑万高铁巴东综合客运枢纽","巴东神农投资有限公司","新建",2020,2026,31220,31220,100,100,0,"建成","建成"]
[2,"恩施市新塘乡综合运输服务站","恩施市新塘乡人民政府","新建",2022,2024,1647,1647,1647,1647,0,"建成","建成"]
[3,"来凤县三胡乡综合运输服务站","来凤天顺实业有限公司","新建",2023,2024,379.5,379.5,379.5,379.5,0,"建成","建成"]
[4,"利川市团堡镇交通综合运输服务站","利川市玉龙运业有限责任公司","新建",2026,2026,350,5,350,5,0,"正式施工","地基平整"]
[5,"南坪乡交通综合运输服务站","利川市南坪客运联营有限公司","新建",2026,2026,320,326.29999999999995,320,326.29999999999995,11.5,"正式施工","完成发光字、电子屏、摄像头、道闸、充电桩、标线及办公家具等设施的安装工作。"]
[6,"咸丰县活龙坪乡综合运输服务站","咸丰县淳毅运输有限公司","新建",2026,2026,400,40,400,40,0,"正式施工","场地平整"]
[]
["合   计",{"$nulls":5},34316.5,33617.8,3196.5,2497.8,11.5]
[null,"单位负责人：                     统计负责人：                     ",{"$nulls":5},"填表人：刘运锋",null,null,"联系电话：0718-8215945",{"$nulls":3},"报出日期：2026年8月25日"]
["填报要求："]
[null,"1、本报表的统计指标解释和统计期同交通部《固定资产投资统计报表制度》；"]
[null,"2、本报表填报的项目为本年度全社会新建、改扩建项目，以前年度结转到本年度的续建项目，已竣工投产但有遗留工程尚未竣工的收尾项目；"]
[null,"3、年报表需经同级交通主管部门审核签章后向上一级运管机构报送。"]